## Sheet1
ID | Work Item Type | Title 1 | Title 2 | Title 3 | State | Tags | Salesforce
90078 | Epic | New Trial Setup |  |  | New | Core Build 1
90097 | Feature |  | Provide a Homepage/Dashboard |  | New | XXL | 160
90219 | User Story |  |  | Ability to land on the application Home Page | New
92979 | User Story |  |  | Create a Clinical Trial Study Maintenance Dashboard | New
94535 | User Story |  |  | Create Protocol Maintenance Dashboard | New
93220 | User Story |  |  | Create an Item Maintenance Dashboard | New
93277 | User Story |  |  | Create a Consignee Maintenance Dashboard | New
93406 | User Story |  |  | Create a Shipper Maintenance Dashboard | New
93715 | User Story |  |  | Create Customer Service Dashboard/Homepage | New
90098 | Feature |  | Create and Add a new Study/Project |  | New | eMDM; XL | 120
90220 | User Story |  |  | Create a new Study/Project with required information | New
92980 | User Story |  |  | Add contact details at Study/Project level | New
92981 | User Story |  |  | Add Notes at Study/Project level | New
97442 | User Story |  |  | Upload and attached study level documents | New
90104 | Feature |  | Create and Add a Protocol within a Study/Project |  | New | eMDM; XL | 120
90279 | User Story |  |  | Add a protocol with all the relevant details | New
92983 | User Story |  |  | Ability to copy details from an existing protocol to a new protocol | New
92984 | User Story |  |  | Add Contacts detail at Protocol Level | New
93196 | User Story |  |  | Add Dangerous Goods (DG) contact details at Protocol Level | New
92985 | User Story |  |  | Add Notes at Protocol Level | New
93003 | User Story |  |  | Ability to place a HOLD at Protocol level | New
97443 | User Story |  |  | Select Specialty Services for a protocol | New
97444 | User Story |  |  | Upload and attached Protocol Level Documents | New
90099 | Feature |  | Add an Item within a Protocol |  | New | XL; TMS; WORLD-STAR | 120
90294 | User Story |  |  | Add an Item to a Protocol with all the required information | New
93222 | User Story |  |  | Select required Item from an Item Table | New
93223 | User Story |  |  | Select required class from classification table | New
93225 | User Story |  |  | Select required Temp_Opt from Temperature Option Table | New
92997 | User Story |  |  | Select required documents from the Documents table | New
92998 | User Story |  |  | Select required packaging from Packaging Table | New
92999 | User Story |  |  | Select required Refrigerant option from Refrigerant Table | New
90306 | User Story |  |  | View an Item overview within a Protocol | New
93000 | User Story |  |  | Add notes to an Item | New
90100 | Feature |  | Add a Consignee to a Protocol |  | New | eMDM; XL | 120 |  | Size | Hours
90310 | User Story |  |  | Create a new Consignee with required information | New
90350 | User Story |  |  | Assign driveaway APC based on the address entered at Consignee Level | New
90334 | User Story |  |  | Add Consignee Primary and Secondary Contacts details | New
93011 | User Story |  |  | Add Consignee DG Emergency Contact details | New
93014 | User Story |  |  | Add notes at Consignee level | New
90348 | User Story |  |  | Ability to bulk upload Consignee Site addresses | New
97496 | User Story |  |  | Attached and Upload required documents for a Consignee | New
90101 | Feature |  | Add a Shipper to a Protocol |  | New | eMDM; XL | 120 |  | S | 40
90308 | User Story |  |  | Create new Shipper with required information | New |  |  |  |  | 60
93429 | User Story |  |  | Assign driveaway APC based on the address entered at Shipper Level | New |  |  |  |  | 80
93017 | User Story |  |  | Add Shipper Investigator details | New |  |  |  |  | 120
93018 | User Story |  |  | Add Shipper Contact details | New |  |  |  |  | 160
97502 | User Story |  |  | Add Shipper DG contact detail | New |  |  |  |  | 200
93020 | User Story |  |  | Display a list of all the shipper contacts within a Protocol | New
93019 | User Story |  |  | Add notes at Shipper level | New
90343 | User Story |  |  | Enter Shipping related instruction for Shipper | New
93081 | User Story |  |  | Ability to bulk upload Shipper Site addressess | New
93716 | User Story |  |  | Add Shipper Notification Checklist | New
93718 | User Story |  |  | Ability to create and print Site instruction | New
93719 | User Story |  |  | Standardize a SITE Instruction for global users | New
97503 | User Story |  |  | Attached and upload required documents at shipper level | New
97531 | User Story |  |  | Enter Shipping Instruction at Shipper Level | New
90103 | Feature |  | Link Item-Consignee pairs to Shippers |  | New | XL | 120 |  | M | 60
90352 | User Story |  |  | Link authorized Items (Commodity+Temp) to applicable Consignees | New
90353 | User Story |  |  | Link Item-Consignee pairs to applicable Shippers | New
90357 | User Story |  |  | Manually bulk link and Unlink Items (Commodity+Temp) to the applicable Consignees and Shippers | New
90354 | User Story |  |  | Have the system assign a default Service Code to each Shipper-Item-Consignee combination | New
90355 | User Story |  |  | Assign one or more Authorized Routes to Shipper-Item-Consignee combinations | New
93087 | User Story |  |  | Add note field for user to enter routing restriction | New
93601 | User Story |  |  | ADD LCT/LPT/RTG details | New
90077 | Epic | Trial and Study Management |  |  | New | Core Build 1
90162 | Feature |  | Ability to make changes at studies/protocol level |  | New | XXL | 160 |  | L | 80
97632 | User Story |  |  | Display a pop-up message if duplicate found | New
90362 | User Story |  |  | Ability to make changes to study level details including other WC offices | New
92990 | User Story |  |  | Ability to approve a Study/Project | New
90221 | User Story |  |  | Drive the status of a Study/Project based on the effective date | New
93082 | User Story |  |  | Ability to make changes at Protocol Level details including other WC offices | New
90283 | User Story |  |  | Drive the status of a Protocol based on the effective date | New
93091 | User Story |  |  | Ability to print SITE instruction with all Consignees | New
90300 | User Story |  |  | Ability to Edit fields related to an Item | New
90301 | User Story |  |  | Ability to Delete an Item from a Protocol | New
90299 | User Story |  |  | Remove packaging or refrigerant from an Item | New | Need Bus Input
90297 | User Story |  |  | Drive the status for the Packaging or Refrigerant of an Item based on the effective date | New | Need Bus Input
90341 | User Story |  |  | Ability to edit fields related to the Shipper/Consignee | New
90338 | User Story |  |  | Inactivate/Re-Activate/Remove a Shipper/Consignee from a study | New | Need Bus Input
90339 | User Story |  |  | Inactivate/Re-activate/Remove Shipper/Consignee Contacts from a study | New | Need Bus Input
93118 | User Story |  |  | Add/update/remove Notes at Study/Protocol/Item/Shipper/Consignee level | New | Need Bus Input
93307 | User Story |  |  | Ability to add an existing Consignee to a Protocol | New
93308 | User Story |  |  | Ability to add an existing Shipper to a Protocol | New
90346 | User Story |  |  | Create/Remove/Update "master" instructions at different inherited levels | New
90163 | Feature |  | Manage HWBs for a study/protocol |  | New | L | 80 |  | XL | 120
90364 | User Story |  |  | Manage and track HWBs | New
90382 | User Story |  |  | Generate and Print Pre-printed HWBs for each Site | New
96843 | User Story |  |  | Create an unique HWB number per job | New
90167 | Feature |  | Maintain Site Pack document templates |  | New | L | 80 |  | XXL | 160
90370 | User Story |  |  | Upload and maintain Site Pack document templates | New
90371 | User Story |  |  | Tailor a Site Pack Template to be Study Specific | New
90372 | User Story |  |  | Save and Maintain the Tailored Study Templates | New |  |  |  |  | 160
90374 | User Story |  |  | Open, Tweak, and Print a Tailored Study Template for a Site | New
90375 | User Story |  |  | Send Site packs by Mail/Email | New
90376 | User Story |  |  | Record and Manage information related to the progress of sending out Site Packs to Sites | New
90106 | Feature |  | Send alert/notification to impacted users only |  | New | Notification Engine; XXL | 160 |  | XXXL | 200
93086 | User Story |  |  | Ability to manage Opt in/Opt out options for email notification | New
90379 | User Story |  |  | Send emails out to Contacts (Single or bulk) for a study | New
90367 | User Story |  |  | Record and Maintain all the communication between customer and CTL | New
90360 | User Story |  |  | Ability to send notification between users within the system (Single and/or groups) | New
90347 | User Story |  |  | Send automated change notifications when changes are made to an Instruction | New
90369 | User Story |  |  | Record and maintain all the customer complaints for a study | New
90340 | User Story |  |  | Send automated change notifications when changes are made to a Shipper/Consignee level | New
90359 | User Story |  |  | Send automated change notifications when changes are made to a Study/Project/Protocol/Item level | New
90358 | User Story |  |  | Configure shipment notifications for a Study | New
90384 | User Story |  |  | Send an Alert when new site address added to a study by CSR during shipment booking | New
93093 | User Story |  |  | Ability to send 'on Demand' notification to all the impacted SITE offices. | New |  |  |  |  | 200
90387 | User Story |  |  | Send Alert to impacted CSR user when making changes to a shipment | New
90388 | User Story |  |  | Send Alert to Impacted CTL users when CSR make changes to a Shipment information | New
90081 | Epic | Shipment Booking and Consolidation |  |  | New | Core Build 1
90174 | Feature |  | Create and submit a shipment for a study |  | New | OOE; TMS; WORLD-STAR; XXL | 160
90385 | User Story |  |  | Create a Booking form for Shipment | New
90383 | User Story |  |  | Add new SITE to a study during Shipment Booking | New
93097 | User Story |  |  | Ability to create parent/child job format | New
93088 | User Story |  |  | Add a routing revision pop-up alert for user | New
90386 | User Story |  |  | Record and Maintain all the changes made by CSR | New
96844 | User Story |  |  | Ability to select packaging from pre-approved List | New
90175 | Feature |  | Shipment consolidation rules for a project |  | New | M | 60
90390 | User Story |  |  | Define shipment consolidation rules sets for projects/Segments (Domestic vs International) | New
90391 | User Story |  |  | Suppress some regularly transmitted fields at any level | New
90091 | Epic | Direct to patient services |  |  | New | Core Build 1
90749 | Feature |  | Direct to Patient (DTP) |  | New | XXL + M | 220
90787 | User Story |  |  | Set DTP service indicator on Bio-STAR | New
90788 | User Story |  |  | Add/Delete DTP service code on Bio-STAR | New
90789 | User Story |  |  | Add/Delete DTP service code on TMS Shipment Screen | New
90791 | User Story |  |  | Transmit DTP fields to Bio-Star integration | New
96839 | User Story |  |  | Flag an item with limited Life Span | New
96842 | User Story |  |  | Special Document handling for DTP services only | New
90080 | Epic | Cell and Gene Therapy services |  |  | New | Core Build 1
90750 | Feature |  | Cell & Gene Therapy |  | New | eMDM; TMS; XXXL + L | 280
90792 | User Story |  |  | Set CGT service indicator on Bio-STAR | New
90793 | User Story |  |  | Add/Delete CGT service code to Bio-STAR | New
90796 | User Story |  |  | Add/Delete CGT service code to TMS Shipment Screen | New
90798 | User Story |  |  | Transmit CGT fields to Bio-Star integration | New
93603 | User Story |  |  | CGT Portal for Client | New
93604 | User Story |  |  | CGT Dashboard/Homepage | New
93605 | User Story |  |  | Tracking CGT shipment | New
97972 | User Story |  |  | Ability to encrypte Confidential Patient Data | New | NFR
90082 | Epic | BioSphere Services |  |  | New | Core Build 1
90751 | Feature |  | BioSphere |  | New | Integrator; XXXL + M | 260 |  | HRS
90768 | User Story |  |  | Set BioSphere Service Indicator on Bio-STAR | New
90772 | User Story |  |  | Add/Delete BioSphere code on Bio-STAR | New
90771 | User Story |  |  | Add/view/Update/Delete Bio-Sphere code on TMS Shipment Screen | New
90786 | User Story |  |  | Transmit BioSphere Field to Bio-Star Integration | New
97865 | User Story |  |  | Display a list of third party integrator for BioSphere | New
97866 | User Story |  |  | Provide an URL link for third party integrator with BioSphere service | New
90083 | Epic | Search and Results |  |  | New | Core Build 1
90178 | Feature |  | Search a study with multiple parameters |  | New | XL | 120 | BUILD | 4000
90393 | User Story |  |  | Ability for global Study search using multiple parameters | New
90222 | User Story |  |  | View details about an existing project | New
90176 | Feature |  | Search Protocol(s) with multiple parameters |  | New | XXL | 160 | BA | 960
90394 | User Story |  |  | Search for a specific Segment across all Projects using multiple parameters | New
90395 | User Story |  |  | See list of search results of the matching Segments and customize as necessary | New
90396 | User Story |  |  | Search for a specific Lane within a Segment or across projects using multiple parameters | New
90397 | User Story |  |  | See list of search results of the matching Lanes and customize as necessary | New
90085 | Epic | Integration |  |  | New | Core Build 1
90181 | Feature |  | Integrate with eMDM |  | New | XXL | 160 | ARCH | 480
90183 | Feature |  | Integrate with Notification Engine |  | New |  |  | TEST | 1200
90184 | Feature |  | Integrate with TMS (By Directional) |  | New | XXL | 160 | DW | 400
[8 empty] | LPTesting | 120
90185 | Feature |  | Integrate with WORLD-STAR (By Directional) |  | New | XXL | 160 | SEC | 400
90186 | Feature |  | Integrate with SSO |  | New | S | 40 |  | 7560
93074 | Feature |  | Integrate with DW(orbis) |  | New | XL | 120
90087 | Epic | Audit Trail |  |  | New | Core Build 1
90190 | Feature |  | Record, Maintain and Track all the changes related to a Study/Protocol/Project |  | New | ORBIS; L | 80
90402 | User Story |  |  | Record, Maintain and Track the history of all the changes relates to a Study | New
90086 | Epic | Reports |  |  | New | Core Build 1
90187 | Feature |  | Generate CTL Reports |  | New | ORBIS; M; TMS; WORLD-STAR | 60
90399 | User Story |  |  | Generate CTL reports with multiple specifications | New
93119 | User Story |  |  | Ability to run DTP/CGT report | New
93121 | User Story |  |  | Run BioSphere report | New
93124 | User Story |  |  | Ability to run New Studies/Protocols report | New
90188 | Feature |  | Generate Sales Reports |  | New | ORBIS; M; TMS; WORLD-STAR | 60
90400 | User Story |  |  | Generate Sales reports with multiple specifications | New
93123 | User Story |  |  | Ability to run Sales report from Bio-STAR | New
90189 | Feature |  | TMS Reports |  | New | ORBIS; M; TMS | 60
90401 | User Story |  |  | Generate Customer reports with multiple specifications | New
93120 | User Story |  |  | Ability to run Transit Detail report from TMS | New
93993 | Epic | Data migration |  |  | New | Core Build 1
93995 | Feature |  | Data migration from WS Bio-STAR to New Bio-STAR |  | New | XXXL + XL | 320
99652 | Epic | Non-Functional Requirements |  |  | New | Core Build 1
99653 | Feature |  | Non-Functional Requirements |  | New | XXL | 160
4000
S | 40
M | 60
L | 80
XL | 120
XXL | 160
XXXL | 200
M | 60
L | 80
XL | 120
XXL | 160
XXXL | 200

## Cost
[8 empty] | LPTesting | 120
| HRS | Rate | Dollar amount | Testing** | Hours | Rate | Dollar amount | SEC | 400
BUILD | 4600 | 100 | 460000 | Functional Testing | 900 | 58 | 52200 |  | 520
BA | 960 | 75 | 72000 | Performance Testing | 150 | 84 | 12600
ARCH | 480 | 143 | 68640 | Validation Testing | 240 | 111 | 26640
TESTING** | 1350 | 80 | 108000 | Penentration testing | 90 | 104 | 9360
DW | 400 | 107 | 42800 | Regression testing | 120 | 60 | 7200
Security | 400 | 100 | 40000 | Dollar amount |  |  | 108000
Project Management* | 350 |  | 35210
Hypercare*** | 272 |  | 32826 | Hypercare*** | Hours | Rate | Dollar amount
| 8812 |  | 859476 | Ruturaaj | 132 | 168 | 22176
|  |  |  | Jeff Rollins | 150 | 71 | 10650
|  |  |  | Dollar amount |  |  | 32826
|  |  |  | Project Management* | Hours | Rate | Dollar amount
|  |  |  | Wajahath Quraishi | 280 | 98 | 27440
|  |  |  | Scicley Christian | 70 | 111 | 7770
|  |  |  | Dollar amount |  |  | 35210

## Schedule
| HRS | Contingency (15%) | Onsite | Offsite | Iteration | No of Onsite resources | Number of Offshore | Total Combined capactity (per iteration) | No of development iterations | Testing ** (Performance/Validation/Regression/Penetration/End to End) | Hypercare
BUILD | 4000 | 4600 | 960 | 1920 | 12 | 1 | 2 | 390 | 12 iterations | 1 iteration
**
Performance Testing
Validation Testing
Penentration testing
Regression testing